## Sheet1
Cost- Benfit analysis
10 years lifetime
Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | TOTALS | Link to Present Value calculator:
Benefits | [12 empty] | http://www.investopedia.com/calculator/pvcal.aspx
Net benefits | 0 | 82260 | 82260 | 82260 | 82260 | 82260 | 82260 | 82260 | 82260 | 82260 | 82260 | 822600
PV of benefits | 0 | 74781.8182 | 67983.4711 | 61803.1555 | 56184.6868 | 51076.988 | 46433.6255 | 42212.3868 | 38374.8971 | 34886.2701 | 31714.791 | 505452.0901
Project information:
NPV of all benefits | 0 | 74781.8182 | 142765.2893 | 204568.4448 | 260753.1316 | 311830.1197 | 358263.7451 | 400476.1319 | 438851.029 | 473737.2991 | 505452.0901 | 3171479.0988 | •Development Staff estimate: man-months | 6 | man-months
•Average cost for 1 Developer for 4 weeks is 25.000kr.
•The new system will increase admin productivity by 37.5% reducing the daily administration time from up to 4 hours to up to 2,5 hours. the value of that is 170,100‬ DKK. each year
•The lifetime of the system is expected to be 10 years
Costs | [12 empty] | •Monthly maintenance costs are estimated : | 5000
One-time costs | 170000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 170000 | •New Hardware cost : | 20000
Recurring costs | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 50000 | •The new system will reduce errors, which is estimated to have a yearly value of : |  |  | 9360 | ( estimate for 1 mistake that would cost 1 hour / week )
•The discount rate is 10%
PV of costs | 170000 | 4545.4545 | 4132.2314 | 3756.574 | 3415.0673 | 3104.6066 | 2822.3697 | 2565.7906 | 2332.5369 | 2120.4881 | 1927.7164 | 200722.8355
NPV of all costs | 170000 | 174545.4545 | 183677.686 | 192434.26 | 200849.3272 | 208953.9338 | 216776.3035 | 224342.0941 | 231674.631 | 238795.1191 | 245722.8355 | 1130460.6615
Overall NPV | -170000 | -99763.6364 | -40912.3967 | 12134.1848 | 59903.8044 | 102876.1858 | 141487.4416 | 176134.0379 | 207176.398 | 234942.18 | 259729.2546 | -135761.858
[13 empty] | Interest Rate : | 10% | Hourly Salary : | 180
[13 empty] | Management cost | 5000 | Work Hrs/Day : | 9
Overall ROI | -1 | -0.57156 | -0.22274 | 0.063056 | 0.29825 | 0.49234 | 0.65269 | 0.78511 | 0.89426 | 0.98387 | 1.057 | 3.4323 | Yearly savings | 82260 | Work Days/Week : | 5
[13 empty] | Hardware Cost | 20000 | Weeks/Year : | 54
[13 empty] | Development Cost | 150000 | Time Saved/Day : | 1.5
[15 empty] | Yearly Salary : | 437400
[15 empty] | Saved Money : | 72900
K = end value
K0 = start value
R = rent (%)
n = total time sequences